## How to
Bookeria pilot tracker
Scenarios tab: one row per test from docs/pilot-test-plan.md. Write your name, the date, the device, then Result: Pass / Fail / Blocked.
If a test fails: add a row in the Problems tab and write its number (P-1, P-2…) in the Problem # column of the scenario.
Severity
A — data wrong or lost, money wrong, someone sees another business's data, booking impossible → tell Claude at once.
B — a feature does not work, but there is a workaround.
C — looks wrong, unclear text, an idea.
Rules
Never write real client names or phone numbers here — describe them ("client with 2 visits").
Copy the page address from the browser into the Page column. Attach screenshots as a link (Google Drive) or paste them into the cell.
Demo site: https://bookeria1.netlify.app — demo accounts in docs/pilot-test-plan.md (password Demo-Bookeria-2026).

## Summary
Scenarios
Total
Pass
Fail
Blocked
Not tested yet
Problems
Open A (must be 0 to move on)
Open B
Open C
Fixed and checked

## Scenarios
Stage | Section | # | Scenario | Expected | Tested by | Date | Device | Language | Result | Problem # | Notes
1 | 1.1 · Client: online booking (phone first) | 1 | Open the salon website, read about, photos, team, hours, map | Everything readable on a phone, Book button visible
1 | 1.1 · Client: online booking (phone first) | 2 | Book "by service": service → any specialist → date → time → name/phone | Confirmation screen with date, time, specialist; booking appears in the owner's calendar
1 | 1.1 · Client: online booking (phone first) | 3 | Book "by specialist" | Only that specialist's services and times
1 | 1.1 · Client: online booking (phone first) | 4 | Two services in one visit | Total time and price add up
1 | 1.1 · Client: online booking (phone first) | 5 | Try a day the salon is closed / a time already taken | Not offered
1 | 1.1 · Client: online booking (phone first) | 6 | Same time from two phones at once | Only one gets it, the other sees "time taken"
1 | 1.1 · Client: online booking (phone first) | 7 | Open the "manage my booking" link from the confirmation; move it; cancel it | Calendar updates; cancelling inside the no-cancel window is refused
1 | 1.1 · Client: online booking (phone first) | 8 | Switch language on the booking page | Everything translated, no English left in Georgian
1 | 1.1 · Client: online booking (phone first) | 9 | Dental clinic booking page | Works the same, clinic theme
1 | 1.1 · Client: online booking (phone first) | 10 | Marketing tick boxes left empty vs ticked | Client card shows consent only when ticked
1 | 1.2 · Staff (specialist) on a phone | 11 | Sign in, see today's own bookings | Only allowed bookings (setting "staff sees all")
1 | 1.2 · Staff (specialist) on a phone | 12 | Open a booking, mark arrived / done / no-show | Status changes everywhere
1 | 1.2 · Staff (specialist) on a phone | 13 | Try to open Settings, reports, export | Refused or hidden
1 | 1.2 · Staff (specialist) on a phone | 14 | Dental doctor: write a treatment note | Saved; staff of the salon can never see it
1 | 1.3 · Admin / reception | 15 | New booking from the calendar for a new client by phone | Client created, phone stored as +995…
1 | 1.3 · Admin / reception | 16 | Move a booking to another time / specialist | Moves; refuses overlaps
1 | 1.3 · Admin / reception | 17 | Block time (lunch, day off) | No online bookings in that time
1 | 1.3 · Admin / reception | 18 | Cancel a booking; waitlist offer by SMS | Freed time offered to waiting clients
1 | 1.3 · Admin / reception | 19 | Checkout: price, discount, payment method | Receipt total correct in ₾, appears in reports
1 | 1.3 · Admin / reception | 20 | Search a client, open the card, history, notes | Correct history
1 | 1.3 · Admin / reception | 21 | Import clients from Excel (use the sample) | Imported without duplicates, no SMS sent
1 | 1.4 · Owner | 22 | Services: add, edit price, variants, hide from online | Booking page updates
1 | 1.4 · Owner | 23 | Team: invite a staff member, set hours, remove | Invite works; removed person can't sign in to this business
1 | 1.4 · Owner | 24 | Business hours, holidays, online booking rules (how far ahead, cancel window, SMS code) | Booking page follows them
1 | 1.4 · Owner | 25 | Website settings: cover, logo, about (3 languages), Instagram, theme | Website changes immediately
1 | 1.4 · Owner | 26 | SMS templates and reminder times | Preview shows the right text
1 | 1.4 · Owner | 27 | Reports: this month, by specialist, Excel download | Numbers match the bookings
1 | 1.4 · Owner | 28 | Export all data (Excel/JSON); delete one client | Export opens; deleted client gone, bookings anonymous
1 | 1.4 · Owner | 29 | Audit log | Shows who did what
1 | 1.4 · Owner | 30 | Allow Bookeria support for 24 h, then end it | Platform admin can look, cannot change anything
1 | 1.4 · Owner | 31 | Sign out of all devices | Other devices signed out on next click
1 | 1.5 · Platform admin (Levan) | 32 | Businesses list, open one, extend trial, add SMS | Saved, written to the business's audit log
1 | 1.5 · Platform admin (Levan) | 33 | Plans: set names and prices | Landing page shows prices once all are set
1 | 1.5 · Platform admin (Levan) | 34 | Sign up a brand-new business from the landing page | Onboarding works end to end (on the demo the email step may not arrive — note it)
1 | 1.6 · General | 35 | Install as an app on the phone ("Add to home screen"), open from the icon
1 | 1.6 · General | 36 | Slow / no internet: clear message, nothing lost
1 | 1.6 · General | 37 | Every page in ka / en / ru — note untranslated or awkward text
1 | 1.6 · General | 38 | Dark mode on the phone
2 | 2 · Production check | 1 | Open bookeria.ge, www.bookeria.ge, bukeria.ge | All reach the landing page over https
2 | 2 · Production check | 2 | Sign up as a new business with your real email | Confirmation email arrives (inbox, not spam)
2 | 2 · Production check | 3 | Password reset; invite a staff member | Emails arrive within a minute
2 | 2 · Production check | 4 | Short address yourtest.bookeria.ge on a phone | Website opens; booking works
2 | 2 · Production check | 5 | Book with your real phone: SMS code, confirmation | SMS arrive within seconds, sender "Bookeria"
2 | 2 · Production check | 6 | Booking for tomorrow + 24 h / 2 h reminders | Reminders arrive on time (up to 5 min late)
2 | 2 · Production check | 7 | SMS balance goes down; admin top-up | Correct counts
2 | 2 · Production check | 8 | Marketing SMS unsubscribe link | Client's consent switched off
2 | 2 · Production check | 9 | Sentry: Claude triggers a test error | Error visible in Sentry
2 | 2 · Production check | 10 | Backups: first daily backup exists; restore test done once | Yes
2 | 2 · Production check | 11 | Two businesses: neither sees the other's data (Claude also runs the automatic isolation tests against production setup) | Yes
2 | 2 · Production check | 12 | Speed: calendar and booking page on a phone over mobile data | Under ~2 s after the first load

## Problems
Problem # | Date | Who | Role used | Device + browser | Language | Page (address) | What I did | What I expected | What happened | Screenshot (link) | Severity | Status | Claude's answer / fix
P-1
P-2
P-3
P-4
P-5
P-6
P-7
P-8
P-9
P-10
P-11
P-12
P-13
P-14
P-15
P-16
P-17
P-18
P-19
P-20
P-21
P-22
P-23
P-24
P-25
P-26
P-27
P-28
P-29
P-30
P-31
P-32
P-33
P-34
P-35
P-36
P-37
P-38
P-39
P-40
P-41
P-42
P-43
P-44
P-45
P-46
P-47
P-48
P-49
P-50
P-51
P-52
P-53
P-54
P-55
P-56
P-57
P-58
P-59
P-60
P-61
P-62
P-63
P-64
P-65
P-66
P-67
P-68
P-69
P-70
P-71
P-72
P-73
P-74
P-75
P-76
P-77
P-78
P-79
P-80
P-81
P-82
P-83
P-84
P-85
P-86
P-87
P-88
P-89
P-90
P-91
P-92
P-93
P-94
P-95
P-96
P-97
P-98
P-99
P-100
P-101
P-102
P-103
P-104
P-105
P-106
P-107
P-108
P-109
P-110
P-111
P-112
P-113
P-114
P-115
P-116
P-117
P-118
P-119
P-120
P-121
P-122
P-123
P-124
P-125
P-126
P-127
P-128
P-129
P-130
P-131
P-132
P-133
P-134
P-135
P-136
P-137
P-138
P-139
P-140
P-141
P-142
P-143
P-144
P-145
P-146
P-147
P-148
P-149
P-150
P-151
P-152
P-153
P-154
P-155
P-156
P-157
P-158
P-159
P-160
P-161
P-162
P-163
P-164
P-165
P-166
P-167
P-168
P-169
P-170
P-171
P-172
P-173
P-174
P-175
P-176
P-177
P-178
P-179
P-180
P-181
P-182
P-183
P-184
P-185
P-186
P-187
P-188
P-189
P-190
P-191
P-192
P-193
P-194
P-195
P-196
P-197
P-198
P-199
P-200